## Slide 1: Systemic and mucosal immune responses of Nile tilapia to monovalent and bivalent vaccines against bacteria Streptococcus agalactiae and Aeromonas veronii.
Quentin ANDRES
MSc. Aquaculture and Aquatic Resources Management @Asian Institute of Technology, Pathum Thani, Thailand
September 2021
MASTER RESEARCH PROJECT PROPOSAL
Notes: Photo on the left from: https://onlinelibrary.wiley.com/doi/abs/10.1111/jfd.12493
Photo on the right: google photos, unspecified.

## Slide 2
Conceptual framework
S
1+2

## Slide 3
WP1 - Pond, fish and husbandry
TASK 1.1: Prepare the 4 aquaria.
TASK 1.2: Assess population distribution parameters
WP3 - Immunization and fish swabs
TASK 1.3: Stock 120 juveniles fish of 12-13 grams per aquarium.
TASK 1.4: Record water parameter.
WP2 - Bacterial preparation, vaccine preparation
TASK 1.6: Acclimate 10 days.
TASK 2.1: Recovery of the two strains
TASK 2.2: Stockage of bacteria for challenge test
TASK 2.3: Production of vaccine Sa
TASK 2.4: Production of vaccine Av
TASK 2.5: Production of vaccine Sa + Av
TASK 2.6: Production of vaccine Control
TASK 3.1: Fish swab before immunization - (baseline IgM)
TASK 3.2: Immunization (Sa, Av, Sa + Av, Control)
TASK 3.3-3.5: Weekly fish swabs to collect biomarkers
WP4 – Lab assays to monitor immune response
TASK 4.1: ELISA for each group of samples for IgM and IgT
TASK 4.2: PCR of key immune genes
TASK 4.3: Agglutination tests
TASK 4.4: Collect and analyse results
TASK 4.5: Draw conclusions
WP5- Challenge test week 4 post vaccination
TASK 5.1: Expose to Steptoccocus agalactiae the group vaccinated with Sa
TASK 5.3: Expose to Aeromonas veronii the group vaccinated with Av
TASK 5.4: Expose to PBS the group vaccinated with Av
WP6 - Ethics requirements
TASK 6.1: Approve use of fish for the study by Animal Care and Use Committee
TASK 5.2: Expose to PBS the group vaccinated with Sa
TASK 6.2: Ensure animal welfare during experimentation
TASK 5.5: Expose to Steptoccocus agalactiae the group vaccinated with Sa + Av
TASK 5.6: Expose to Aeromonas veronii the group vaccinated with Sa + Av
TASK 5.7: Expose to PBS the group vaccinated with Sa + Av
TASK 5.9: Draw conclusions
TASK 5.8: Daily monitoring survival rate
TASK 1.5: Define feeding regime.
TASK 1.7: Bacterial isolation: fish is free of diseases
TASK 3.6: Immunization booster (Sa, Av, Sa + Av, Control)
TASK 3.7-3.14: Weekly fish swabs to collect biomarkers
WP5’- Challenge test (end of experiment)
TASK 5.1: Expose to Steptoccocus agalactiae the group vaccinated with Sa
TASK 5.2: Expose to PBS the group vaccinated with Sa
TASK 5.3: Expose to Aeromonas veronii the group vaccinated with Av
TASK 5.4: Expose to PBS the group vaccinated with Av
TASK 5.5: Expose to Steptoccocus agalactiae the group vaccinated with Sa + Av
TASK 5.6: Expose to Aeromonas veronii the group vaccinated with Sa + Av
TASK 5.7: Expose to PBS the group vaccinated with Sa + Av
TASK 5.8: Daily monitoring survival rate
TASK 5.9: Draw conclusions
Work packages
and tasks
AT RISK
NOT STARTED
ON-GOING
COMPLETED

## Slide 4
Prepare pond, stock breeders, select feeding regime
Feed the offspring and raise 400 juveniles
Prepare 4 medium experimental ponds for Ct, Sa, Av, Sa+Av
WP1 - Pond, fish and husbandry
WP2 - Bacterial preparation, vaccine preparation
WP3 - Immunization, fish swab
WP4 - Lab assays to monitor immune response
WP5 – Challenge tests
Recovery of the two bacterial strains, amplification and culture
Fish swab before immunization - baseline biomarkers titers
ELISA for IgM and IgT
Expose unvaccinated group to Av
Production of vaccine Sa
Production of vaccine Av
Production of vaccine Sa+Av
Production of vaccine Control (PBS)
Immunization (Sa, Av, Sa + Av, Control)
Quality control, fish free of diseases
Baseline biomarkers titers before challenge test
Weekly fish swabs to collect biomarkers
PCR of key immune genes
Agglutination test
Collect and analyse results
Prepare at least 9 small ponds for the challenge test
Stockage of bacteria for challenge test
Quality control, fish free of diseases
Expose to Av strain the group vaccinated with Av
Expose to Sa strain the group vaccinated with Sa
Expose to Sa strain the group vaccinated with Sa+Av
Expose to Av strain the group vaccinated with Sa+Av
ELISA for IgM and IgT
PCR of key immune genes
Agglutination test
Daily monitoring survival rate
Acclimation 10-14 days
Control groups
Perform challenge test 1 (week4 pv)
Expose unvaccinated group to Sa
Draw conclusions
Perform challenge test 2 (week 12 pv)
Workflow and work
packages
Experimental design ->

## Slide 5
Group SaAv
Vaccinated tilapia (Sa+Av)
n = 165 fish
m = 13 ± 2g
Group Sa
Vaccinated tilapia (Sa)
n = 165 fish
m = 13 ± 2g
Group Av
Vaccinated tilapia (Av)
n = 165 fish
m = 13 ± 2g
Group PBS
Un-vaccinated tilapia (PBS)
n = 165 fish
m = 13 ± 2g
Bacterial isolation
Sa-free & Av-free
Acclimatation 10 days at RT
First vaccination (day 0) &
Second vaccination
(day 21)
Challenge
(week 4)
Injection 100u IP vaccine
Injection 100u IP vaccine
Injection 100u IP vaccine
Injection 100u IP
PBS
Subgroup SaAv 1
N = 60
Subgroup SaAv 2
N = 60
Subgroup
Sa 1
N = 60
Subgroup Sa 2
N = 60
SubgroupAv 1
N = 60
Subgroup Av 2
N = 60
Subgroup
PBS 1
N = 60
Subgroup PBS 2
N = 60
+Sa 4
N =15
+Sa
10^6C/ml IP
+Av
10^6C/ml IP
+Sa 4’
N =15
+Sa 12
N =15
+Sa 12’
N =15
+Av 4
N =15
+Av 4’
N =15
+Av 12
N =15
+Av 12’
N =15
Challenge
(week 12)
Challenge
(week 4)
Challenge
(week 12)
+Sa 4
N =15
+Sa 4’
N =15
+Sa 12
N =15
+Sa 12’
N =15
+Av 4
N =15
+Av 4’
N =15
+Av 12
N =15
+Av 12’
N =15
+Sa 4
N =15
+Sa 4’
N =15
+Sa 12
N =15
+Sa 12’
N =15
+Av 4
N =15
+Av 4’
N =15
+Av 12
N =15
+Av 12’
N =15
Examine fish and feed 3%BW
Record events / abnormalities
Sampling:
Blood & mucus ELISA for IgM levels. N=8fish/tank
Head kidney & spleen PCR for gene expression
N=3 fish/tank
Every week for 12 weeks
Record events / abnormalities
Record mortality
Remove dead fish
Move subgroup to challenge tanks
At 12 weeks p.v.
m = 20 ± 2g

## Slide 6
August |  |  | September |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Oct | 
Dates | 2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
Project Day | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Project Week |  |  |  |  |  |  |  |  |  | S | T | A | R | T | 1 |  |  |  |  |  |  | 2 |  |  |  |  |  |  | 3 |  |  |  |  | 
Phase one |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Conception Definition Planning Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Two |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pond/fish Bacterial recovery Bacterial preparation Fish swabs Immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Three |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Challenge tests Lab assays ELISA & PCR Bacteriology Draw results Conclusions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Planning Timeline
Main Review
Initiation
Scope and Goal Setting
Work Bkdwn Structure
Immunization 1
Bacterial isolation on 5 fish.
Fish swabs 1
Fish swabs 2
Culture bacteria
Prepare ponds and acclimate 7 days
Recover the two bacterial strains 1 day
Produce vaccine
Today

## Slide 7
September |  |  | October |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov | 
Dates | 2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
Project Day | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Project Week |  |  |  |  |  | 3 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 5 |  |  |  |  |  |  | 6 |  |  |  |  |  |  | 7
Phase one |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Conception Definition Planning Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Two |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pond/fish Bacterial recovery Bacterial preparation Fish swabs Immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Three |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Challenge tests Lab assays ELISA & PCR Bacteriology Draw results Conclusions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Planning Timeline
Fish swabs 3
Fish swabs 4
Fish swabs 6
F
Immunization 2 Booster of day 21
First bacterial challenge
Fish swabs 5

## Slide 8
October |  |  | November |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Dec | 
Dates | 2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
Project Day | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Project Week |  |  | 7 |  |  |  |  |  |  | 8 |  |  |  |  |  |  | 9 |  |  |  |  |  |  | 10 |  |  |  |  |  |  | 11 |  |  | 
Phase one |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Conception Definition Planning Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Two |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pond/fish Bacterial recovery Bacterial preparation Fish swabs Immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Three |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Challenge tests Lab assays ELISA & PCR Bacteriology Draw results Conclusions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Planning Timeline
Fish swabs 7
Fish swabs 8
Fish swabs 9
Fish swabs 10
Fish swabs 11

## Slide 9
November |  |  | December |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Jan | 
Dates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2022 | 
 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | C | 30 | 31 | 1
Project Day | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Project Week | 11 |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 13 |  |  |  |  |  |  | 14 |  |  |  |  |  |  | 15 |  |  | E | N | D
Phase one |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Conception Definition Planning Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase Two |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | P
Pond/fish Bacterial recovery Bacterial preparation Fish swabs Immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | O
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | J
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | E
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C
Phase Three |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T
Challenge tests Lab assays ELISA & PCR Bacteriology Draw results Conclusions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | E
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | N
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D
Project Planning Timeline
Fish swabs 12
Fish swabs 11
ELISA
Agglutination
PCR
Second bacterial challenge
Lab assays to monitor immune responses
Draw results
Conclude

## Slide 10
Thank you !