## WPs descriptions
1 |  |  | 2
WORK PACKAGE DESCRIPTION |  |  | WORK PACKAGE DESCRIPTION
WP code: WP-1 | WP1 - Pond, fish and husbandry |  | WP code: WP-2 | WP2 - Bacterial preparation, vaccine preparation
Goals: |  |  | Goals:
Content: | T1.1 | Prepare pond, stock breeders, select feeding regime | Content: | T2.1 | Recovery of the two strains, amplification and culture
| T1.2 | Feed the offspring and raise 400 juveniles. |  | T2.2 | Stockage of bacteria for challenge test
| T1.3 | Quality control, fish free of diseases |  | T2.3 | Production of vaccine Sa
| T1.4 | Prepare 4 medium experimental ponds for Ct, Sa, Av, SaAv |  | T2.4 | Production of vaccine Av
| T1.5 | Acclimatation 10-14 days |  | T2.5 | Production of vaccine Sa + Av
| T1.6 | Prepare at least 9 small ponds for the challenge test |  | T2.6 | Production of vaccine Control
| T1.7 | Clean the ponds at the end of the experiment
Expected Results | . . . |  | Expected Results | . . .
Resources |  |  | Resources
Raw material |  |  | Raw material
Lab facilities |  |  | Lab facilities
Dependencies |  |  | Dependencies
3 |  |  | 4
WORK PACKAGE DESCRIPTION |  |  | WORK PACKAGE DESCRIPTION
WP code: WP-3 | WP3 - Immunization, fish swab |  | WP code: WP-4 | WP4 - Lab assays to monitor immune response
Goals: |  |  | Goals:
Content: | T3.1 | Fish swab before immunization - (baseline IgM IgT titers) | Content: | T4.1 | ELISA for each group of samples for IgM and IgT
| T3.2 | Immunization (Sa, Av, Sa + Av, Control) |  | T4.2 | PCR of key immune genes
| T3.3 | Weekly fish swabs (to collect biomarkers) |  | T4.3 | Agglutination test
|  |  |  | T4.4 | Collect and analyze results
|  |  |  | T4.5 | Draw conclusions
Expected Results | . . . |  | Expected Results | . . .
Resources |  |  | Resources
Raw material |  |  | Raw material
Lab facilities |  |  | Lab facilities
Dependencies |  |  | Dependencies
5 |  |  | 6
WORK PACKAGE DESCRIPTION |  |  | WORK PACKAGE DESCRIPTION
WP code: WP-5 | WP5 - Challenge test |  | WP code: WP-6 | WP6 - Ethics requirements
Goals: |  |  | Goals:
Content: | T5.1 | Expose to Steptoccocus agalactiae the group vaccinated with Sa | Content: | T6.1 | Ethics requirement 1: Animal welfare during experimentation
| T5.2 | Expose to PBS the group vaccinated with Sa |  | T6.2 | Ethics requirement 2: Approve use of fish for the study by Animal Care and Use Committee
| T5.3 | Expose to Aeromonas veronii the group vaccinated with Av
| T5.4 | Expose to PBS the group vaccinated with Av
| T5.5 | Expose to Steptoccocus agalactiae the group vaccinated with Sa + Av
| T5.6 | Expose to Aeromonas veronii the group vaccinated with Sa + Av
| T5.7 | Expose to PBS the group vaccinated with Sa + Av
| T5.8 | Draw conclusions
Expected Results | . . . |  | Expected Results | . . .
Resources |  |  | Resources
Raw material |  |  | Raw material
Lab facilities |  |  | Lab facilities
Dependencies |  |  | Dependencies

## WPs high level delivery roadmap
|  |  | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY
Work Packages
WP-1 |  | Initiate project
| TASK 1-A | Wrap-up project overview (ppt?)
| TASK 1-B | Find collaborating research units
| TASK 1-C | Find master thesis supervisor
| TASK 1-D | Assess raw material and lab facilities needs
| TASK 1-E | Assess project cost estimates
| TASK 1-F | Find funding
WP-2 |  | Review relevant literature
| TASK 2-A | Enter Name
| TASK 2-B | Enter Name
| TASK 2-C | Enter Name
| TASK 2-D | Enter Name
| TASK 2-E | Enter Name
| TASK 2-F | Enter Name
WP-3 |  | Biocomputational design
| TASK 3-A | Enter Name
| TASK 3-B | Enter Name
| TASK 3-C | Enter Name
| TASK 3-D | Enter Name
| TASK 3-E | Enter Name
| TASK 3-F | Enter Name
WP-4 |  | Vaccine production
| TASK 4-A | Protocols & execution
| TASK 4-B | Protocols & execution
TASK 4-C
TASK 4-D
| TASK 4-E | Enter Name
| TASK 4-F | Introduce fluoluminescence ?
WP-5 |  | Challenge tests
| TASK 5-A | Carp culture
| TASK 5-B | Challenge test protocol - survival rate
TASK 5-C
| TASK 5-D | Challenge test protocol - fluoluminescence ?
TASK 5-E
| TASK 5-F | Enter Name
WP-6 |  | Master thesis writing and communications
| TASK 6-A | Writing Literature review
| TASK 6-B | Writing Chapter 1 -
| TASK 6-C | Writing Chapter 2 -
| TASK 6-D | Monthly status PPT
| TASK 6-E | Writing Chapter 3 -
| TASK 6-F | Introduction/Conclusion/Acknowledgement