## Sheet1
PLANNING |  | AUG |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV
WP |  | 2009-08-01 |  |  | 1930-08-01 |  |  |  |  | 2004-10-01 |  |  |  | 2001-11-01
Task | Tasks/Dates | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47
WP0 - Master thesis prep
T0.1 | Proposal
T0.2 | First draft
T0.3 | Final draft
T0.4 | Regular check
WP1 - Pond, fish and husbandry
T1.1 | Prepare pond, stock breeders, select feeding regime | bar: 1930-08-01 W35 to 2004-10-01 W41
T1.2 | Feed the offspring and raise 400 juveniles. | bar: 1930-08-01 W37 to 2004-10-01 W41
T1.3 | Quality control, fish free of diseases | bar: 2004-10-01 W41
T1.4 | Prepare 4 medium experimental ponds for Ct, Sa, Av, SaAv | bar: 2004-10-01 W42
T1.5 | Acclimatation 10-14 days | bar: 2004-10-01 W42 to 2004-10-01 W43
T1.6 | Prepare at least 9 small ponds for the challenge test
T1.7 | Clean the ponds at the end of the experiment
WP2 - Bacterial preparation, vaccine preparation
T2.1 | Recovery of the two strains, amplification and culture
T2.2 | Stockage of bacteria for challenge test
T2.3 | Production of vaccine Sa
T2.4 | Production of vaccine Av
T2.5 | Production of vaccine Sa + Av
T2.6 | Production of vaccine Control
WP3 - Immunization, fish swab
T3.1 | Fish swab before immunization - (baseline IgM IgT titers)
T3.2 | Immunization (Sa, Av, Sa + Av, Control)
T3.3 | Weekly fish swabs (to collect biomarkers)
WP4 - Lab assays to monitor immune response
T4.1 | ELISA for each group of samples for IgM and IgT
T4.2 | PCR of key immune genes
T4.3 | Agglutination test
T4.4 | Collect and analyze results
T4.5 | Draw conclusions
WP5 - Challenge test
T5.1 | Expose to Steptoccocus agalactiae the group vaccinated with Sa
T5.2 | Expose to PBS the group vaccinated with Sa
T5.3 | Expose to Aeromonas veronii the group vaccinated with Av
T5.4 | Expose to PBS the group vaccinated with Av
T5.5 | Expose to Steptoccocus agalactiae the group vaccinated with Sa + Av
T5.6 | Expose to Aeromonas veronii the group vaccinated with Sa + Av
T5.7 | Expose to PBS the group vaccinated with Sa + Av
T5.8 | Draw conclusions
WP6 - Ethics requirements
T6.1 | Ethics requirement 1: Animal welfare during experimentation
T6.2 | Ethics requirement 2: Approve use of fish for the study by Animal Care and Use Committee
PLANNING (continued) |  | 2009-08-01 W32: DEC; 1930-08-01 W36: JAN; 2004-10-01 W41: FEB; 2001-11-01 W45: MAR
WP |  | 2009-08-01 W33: 2006-12-01; 1930-08-01 W36: 2027-12-01; 2004-10-01 W41: 1931-01-01; 2001-11-01 W45: 2028-02-01
Task | Tasks/Dates | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11
WP0 - Master thesis prep
T0.1 | Proposal
T0.2 | First draft
T0.3 | Final draft
T0.4 | Regular check
WP1 - Pond, fish and husbandry
T1.1 | Prepare pond, stock breeders, select feeding regime
T1.2 | Feed the offspring and raise 400 juveniles.
T1.3 | Quality control, fish free of diseases
T1.4 | Prepare 4 medium experimental ponds for Ct, Sa, Av, SaAv
T1.5 | Acclimatation 10-14 days
T1.6 | Prepare at least 9 small ponds for the challenge test
T1.7 | Clean the ponds at the end of the experiment
WP2 - Bacterial preparation, vaccine preparation
T2.1 | Recovery of the two strains, amplification and culture
T2.2 | Stockage of bacteria for challenge test
T2.3 | Production of vaccine Sa
T2.4 | Production of vaccine Av
T2.5 | Production of vaccine Sa + Av
T2.6 | Production of vaccine Control
WP3 - Immunization, fish swab
T3.1 | Fish swab before immunization - (baseline IgM IgT titers)
T3.2 | Immunization (Sa, Av, Sa + Av, Control)
T3.3 | Weekly fish swabs (to collect biomarkers)
WP4 - Lab assays to monitor immune response
T4.1 | ELISA for each group of samples for IgM and IgT
T4.2 | PCR of key immune genes
T4.3 | Agglutination test
T4.4 | Collect and analyze results
T4.5 | Draw conclusions
WP5 - Challenge test
T5.1 | Expose to Steptoccocus agalactiae the group vaccinated with Sa
T5.2 | Expose to PBS the group vaccinated with Sa
T5.3 | Expose to Aeromonas veronii the group vaccinated with Av
T5.4 | Expose to PBS the group vaccinated with Av
T5.5 | Expose to Steptoccocus agalactiae the group vaccinated with Sa + Av
T5.6 | Expose to Aeromonas veronii the group vaccinated with Sa + Av
T5.7 | Expose to PBS the group vaccinated with Sa + Av
T5.8 | Draw conclusions
WP6 - Ethics requirements
T6.1 | Ethics requirement 1: Animal welfare during experimentation
T6.2 | Ethics requirement 2: Approve use of fish for the study by Animal Care and Use Committee